## Runbook
ID | Phase | Domain | Steps | Dependency | Interface-ID | Steps Detail | Time | Artifact | Pipeline | Owner | Remark | Dev | Test | UAT | Prod
| Pre-Deployment | Azure Resources | SFTP Connection |  | KH-KBS-002 | Create Coupa SFTP connection |  | SFTP connection name | Manual | DevOpsLead | Ignore if already created | SFTP connection name= sftpwithssh-1 | SFTP connection name = sftpwithssh-5
| Pre-Deployment | Azure Resources | Service Bus - Topic and Subscription Name |  | KH-KBS-002 | Create the Service Bus topic and subscription |  | Service bus topic and subscription name | Manual | DevOpsLead | Ignore if already created | Service bus namespace = kh-neu-dev Service bus topic name = kh-kbs-009-invoicepaymentdetails Service bus subscription name = postinvoicepaymentdetails | Service bus namespace = kh-neu-test Service bus topic name = kh-kbs-009-invoicepaymentdetails Service bus subscription name = postinvoicepaymentdetails | Service bus namespace = sb-neu-uat-01 Service bus topic name = kh-kbs-009-invoicepaymentdetails Service bus subscription name = postinvoicepaymentdetails | Service bus namespace = kh-neu-prd Service bus topic name = kh-kbs-009-invoicepaymentdetails Service bus subscription name = postinvoicepaymentdetails Service bus namespace = kh-weu-prd Service bus topic name = kh-kbs-009-invoicepaymentdetails Service bus subscription name = postinvoicepaymentdetails
| Pre-Deployment | Azure Resources | Service Bus Connection |  | KH-KBS-002 | Create the Service Bus API Connection |  | Service bus connection name | Manual | DevOpsLead | Ignore if already created | Service bus connection name = servicebus-1 | Service bus connection name = servicebus-1
| Pre-Deployment | Azure Resources | Storage Account Name | KH-Team | KH-KBS-002 | Get the storage account name for the log collector |  | Storage account name | Manual | DevOpsLead |  | Storage account name = saneudevkhstd01 | Storage account name = saneutestkhstd01 | Storage account name = saneuuatkhstd01 | Storage account name = saneuprdkhstd01 (neu-prd) Storage account name = saweuprdkhstd01 (weu-prd)
| Pre-Deployment | Azure Resources | Storage Account Connection | KH-Team | KH-KBS-002 | Get the storage account connection name for the log collector |  | Storage account connection name | Manual | DevOpsLead |  | Storage account connection name = kh-logging-stg-conn | Storage account connection name = kh-logging-stg-conn | Storage account connection name = kh-logging-stg-conn | Storage account connection name = kh-logging-stg-conn
| Pre-Deployment | Azure Resources | Encrypt-Decrypt function App Endpoint API URI and Subscription key | KH-Team | KH-KBS-002 | Get the Function App Endpoint API URI for the log collector |  | API URI and Subscription key | Manual | DevOpsLead |  | API URI secret name = ApimUrl API Sub Key secret name = Apim-Subscription-Key-enterprise-components | API URI secret name = ApimUrl API Sub Key secret name = Apim-Subscription-Key-enterprise-components | API URI secret name = ApimUrl API Sub Key secret name = Apim-Subscription-Key-enterprise-components | API URI secret name = ApimUrl API Sub Key secret name = Apim-Subscription-Key-enterprise-components
| Pre-Deployment | Azure Resources | Update Cross Ref API URI's | KH-Team | KH-KBS-002 | Verify whether the URI's are pointing to the respective environments |  |  | Manual | DevOpsLead |  | Publisher crossRefAPIURI=https://api-nonprod-groupservices.kantar.com/test/kantarhub-enterprise-data/v1/refdata Subscriber crossRefAPIURI=https://api-nonprod-groupservices.kantar.com/test/kantarhub-enterprise-data/v1/refdata?DataDomain=S2P - Country&SystemA=Coupa&SystemB=Maconomy&SystemAField1=Country&SystemBField1=Country | Publisher crossRefAPIURI=https://api-nonprod-groupservices.kantar.com/test/kantarhub-enterprise-data/v1/refdata Subscriber crossRefAPIURI=https://api-nonprod-groupservices.kantar.com/test/kantarhub-enterprise-data/v1/refdata?DataDomain=S2P - Country&SystemA=Coupa&SystemB=Maconomy&SystemAField1=Country&SystemBField1=Country
| Pre-Deployment | Azure Resources | Update system URI's (maconomy and coupa URI's) | KH-Team | KH-KBS-002 | Verify whether the system URI's are pointing to the respective environments |  |  | Manual | DevOpsLead |  | JobsAPIURI=https://kantar-d05.deltekenterprise.com/containers/v1/kantd05/kantar:find_KAN_Jobs/filter TokenURI (for maconomy interfaces) = https://api-nonprod-groupservices.kantar.com/dev/maconomy/v1/reconnect-token TaskListURI=https://kantar-d05.deltekenterprise.com/containers/v1/kantd05/find_tasklistline/filter ConcurrencyControlURI=https://kantar-d05.deltekenterprise.com/containers/v1/kantd05/jobs/data;jobnumber= jobsUpdateURI=https://kantar-d05.deltekenterprise.com/containers/v1/kantd05/jobs/data;jobnumber= | JobsAPIURI=https://kantar-t03.deltekenterprise.com/containers/v1/kantt03/kantar:find_KAN_Jobs/filter TokenURI (for maconomy interfaces) = https://api-nonprod-groupservices.kantar.com/test/maconomy/v1/reconnect-token TaskListURI=https://kantar-t03.deltekenterprise.com/containers/v1/kantt03/find_tasklistline/filter ConcurrencyControlURI=https://kantar-t03.deltekenterprise.com/containers/v1/kantt03/jobs/data;jobnumber= jobsUpdateURI=https://kantar-t03.deltekenterprise.com/containers/v1/kantt03/jobs/data;jobnumber=
| Pre-Deployment | Azure Resources | Kantar PGP Key | KH-Team | KH-KBS-002 | Update the Kantar Hub PGP Keys in the Key vault PGP-Public-Key-Coupa-Encoded PGP-Public-Key-KantarHub-Encoded PGP-Primary-PassPhrase-KantarHub PGP-Primary-Private-Key-KantarHub-Encoded PGP-Secondary-PassPhrase-KantarHub PGP-Secondary-Private-Key-KantarHub-Encoded |  | PGP-Public-Key-Coupa-Encoded PGP-Public-Key-KantarHub-Encoded PGP-Primary-PassPhrase-KantarHub PGP-Primary-Private-Key-KantarHub-Encoded PGP-Secondary-PassPhrase-KantarHub PGP-Secondary-Private-Key-KantarHub-Encoded | Manual | DevOpsLead | Ignore if already Updated in Key vault | KV name = KV-BSTVAULT-DEV-NEU-01 Secret names = PGP-Public-Key-Coupa-Encoded PGP-Public-Key-KantarHub-Encoded PGP-Primary-PassPhrase-KantarHub PGP-Primary-Private-Key-KantarHub-Encoded PGP-Secondary-PassPhrase-KantarHub PGP-Secondary-Private-Key-KantarHub-Encoded | KV name = kv-bstvault-test-neu-01 Secret names = PGP-Public-Key-Coupa-Encoded PGP-Public-Key-KantarHub-Encoded PGP-Primary-PassPhrase-KantarHub PGP-Primary-Private-Key-KantarHub-Encoded PGP-Secondary-PassPhrase-KantarHub PGP-Secondary-Private-Key-KantarHub-Encoded | KV name = kv-bstvault-uat-neu-01 Secret names = PGP-Public-Key-Coupa-Encoded PGP-Public-Key-KantarHub-Encoded PGP-Primary-PassPhrase-KantarHub PGP-Primary-Private-Key-KantarHub-Encoded PGP-Secondary-PassPhrase-KantarHub PGP-Secondary-Private-Key-KantarHub-Encoded | KV name = kv-bstvault-prd-neu-01 Secret names = coupaAPISubKey crossrefdataapisubkey MeconomyAPISubKey KV name = kv-bstvault-prd-weu-01 Secret names = coupaAPISubKey crossrefdataapisubkey MeconomyAPISubKey
| Pre-Deployment | Key vault secrets | Key vault configuration |  | KH-KBS-002 | Update the below secret names in key vault coupaAPISubKey crossrefdataapisubkey MeconomyAPISubKey |  | crossrefdataapisubkey reconnectTokenKey | Manual | DevOpsLead | Ignore if already Updated in Key vault | KV name = KV-BSTVAULT-DEV-NEU-01 Secret names = crossrefdataapisubkey reconnectTokenKey | KV name = kv-bstvault-test-neu-01 Secret names = crossrefdataapisubkey reconnectTokenKey | KV name = kv-bstvault-uat-neu-01 Secret names = reconnectTokenKey crossrefdataapisubkey | KV name = kv-bstvault-prd-neu-01 Secret names = crossrefdataapisubkey reconnectTokenKey KV name = kv-bstvault-prd-weu-01 Secret names = crossrefdataapisubkey reconnectTokenKey
| Pre-Deployment | Repository | Review branch and project structure |  | KH-KBS-002 | Repo:KH.Coupa Branch:KH-KBS-002-AccountMasterData-Release1 Source Path:https://kantarware.visualstudio.com/KantarIntegrationPlatform/_git/KH.Coupa?version=GBKH-KBS-002-AccountMasterData-Release1 Verify that the code is checked in properly into the KH-KBS-002-AccountMasterData-Release1 branch under the KH.Coupa repository and aligned to the kantar project structure |  |  | Manual | DevOpsLead |  | Repo:KH.Coupa Branch:KH-KBS-002-AccountMasterData-Release1 | Repo:KH.Coupa Branch:KH-KBS-002-AccountMasterData-Release1 | Repo:KH.Coupa Branch:KH-KBS-002-AccountMasterData-Release1 | Repo:KH.Coupa Branch:KH-KBS-002-AccountMasterData-Release1
| Pre-Deployment | Repository | Update parameter file and yaml files |  | KH-KBS-002 | Update below parameters with correct values in the parameter files environment primaryregion shortLocation keyVaultName frequency interval resourceGroup Update below parameters in KH-KBS-009-InvoicePayment-Publish-01-pipeline and KH-KBS-009-InvoicePayment-Coupa-Subsciber-01 yaml pipelines Branch name Repo Solution and Project name Stages environment resourceGroupName logicAppName folderName logicAppProject logicAppParameters azureResourceManagerConnection subscriptionId location triggerName keyVaultName integrationAccountName integrationAccountResourceGroupName maps |  |  | Manual | DevOpsLead |  | LogicApp.parameters.dev.json | LogicApp.parameters.test.json | LogicApp.parameters.uat.json | LogicApp.parameters.prd-neu.json LogicApp.parameters.prd-weu.json
| Deployment | Logic app deployment |  |  | KH-KBS-002 | Verify and run the pipelines KH-KBS-002-AccountMasterPublisher and KH-KBS-002-AccountMasterSubscriber |  |  | KH-KBS-002a-AccountMasterPublisher KH-KBS-002a-AccountMasterSubscriber | DevOpsLead |  | Logic apps = kh-kbs-002-la-neu-dev-getjobdatafrommaconomy kh-kbs-002-la-neu-dev-postjobtaskdatatocoupa | Logic apps = kh-kbs-002-la-neu-test-getjobdatafrommaconomy kh-kbs-002-la-neu-test-postjobtaskdatatocoupa
| Smoke Testing |  |  |  | KH-KBS-002 | Verify the Logic apps deployment and Test using postman |  |  | Manual | DevOpsLead
| Smoke Testing |  |  |  | KH-KBS-002 | Verify whether the Logic apps are consuming the correct keys and endpoints (corresponding to respective environment) in all the places that we have configured |  |  | Manual | DevOpsLead
| Smoke Testing |  |  |  | KH-KBS-002 | Verify the Logic apps consuming the correct Service bus connection,SFTP Connection,Functions and maps |  |  | Manual | DevOpsLead
| Rollback plan |  |  |  | KH-KBS-002 | For First time of deployment, we are following the below steps to rollback 1.Delete logic apps kh-kbs-002-la-neu-dev-getjobdatafrommaconomy and kh-kbs-002-la-neu-dev-postjobtaskdatatocoupa 2.Delete maps KH-KBS-002-mp-neu-dev-Job-MaconomyToCoupa-Lookup.liquid and KH-KBS-002-mp-neu-dev-Task-MaconomyToCoupa-Lookup.liquid |  |  | Manual | DevOpsLead

## Screenshot
ID | ScreenShot

## ContactDetails
Team Name | Person name | Email
Development Team | Shubraja AH | vaibhav.nalawade.cognizant@kantar.com
Development Team | Goudar, Ashok | ashok.goudar.cognizant@kantar.com